## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Sandhiya R | Day 2 | confusion in selecting correct approach | Sprint 1 | Sandhiya R | Logical | compared techniques and finalized resnet50 | Day 3 | Closed | resolved after research
2 | Sandhiya R | Day 5 | dataset not loading properly | sprint 2 | Sandhiya R | Logical | fixed file path and directory structure | DAY 5 | Closed | issue resolved
3 | Sandhiya R | Day 5 | corrupted images causing errors | Sprint 2 | Sandhiya R | Data | removed invaled images | Day 6 | Closed | Dataset cleaned
4 | Sandhiya R | Day 10 | low model accuracy | Sprint 3 | Sandhiya R | Logical | tuned hyperparameters | Day 11 | Closed | Accuracy improved
5 | Sandhiya R | Day 11 | low model accuracy | Sprint 3 | Sandhiya R | Logical | added droupout and regularization | Day 12 | Closed | Model improved
1 | S.Maheswari | Day 2 | dataset not loading properly | Sprint 1 | Maheswari S | Data | directly downloaded to notebook using kaggle commands | Day 3 | Closed | Resolved after correcting dataset paths
2 | S.Maheswari | Day 4 | Images not clear for text detection | Sprint 2 | Maheswari S | Logical | Applied preprocessing | Day 5 | Closed | Image clarity improved
3 | S.Maheswari | Day 5 | Poor visibility in images | Sprint 2 | Maheswari S | Logical | Applied thresholding to enhance text | Day 6 | Closed | Text visibility enhanced
4 | Bhargavi K | Day 9 | low model accuracy during training | Sprint 3 | Bhargavi K | Logical | Increased epochs and applied data augmentation | Day 10 | Closed | Accuracy improved
5 | Bhargavi K | Day 11 | Training time too high | Sprint 3 | Bhargavi K | Logical | migrated execution from CPU to GPU in Google Colab for improved performance | Day 12 | Closed | Training time optimized
6 | Deeksha H L | Day 2 | Dataset path error | Sprint 1 | Deeksha H L | Logical | Corrected file path | Day 3 | Closed | Issue resolved
7 | Deeksha H L | Day 5 | images not loading | Sprint 2 | Deeksha H L | User Interface | Fixed images display issue | Day 5 | Closed | Working fine
8 | Devi P | Day 5 | Corrupted images | Sprint 2 | Devi P | Maintainability | Cleaned dataset | Day 6 | Closed | Dataset improved
9 | Devi P | Day 10 | low model accuracy | Sprint 3 | Devi P | Logical | Applied augmentation | Day 11 | Closed | Accuracy improved
10 | Pravalli l | Day 11 | High training time | Sprint 3 | Pravalli l | Maintainability | Optimized training process | Day 12 | Closed | Faster training
11 | Pravalli l | Day 12 | Threshold issue | Sprint 3 | Pravalli l | Standards | Applied threshold tuning | Day 12 | Closed | Faster training
13 | Fariyal Jamadar | Day 1 | data preprocessing | Sprint 1 | Fariyal J | Logical | Cleaned dataset | Day 6 | Closed | issue resolved
14 | Fariyal Jamadar | Day 12 | Functional Defect | Sprint 2 | Fariyal J | Logical | OCR fails | Day 13 | Closed | issue resolved
15 | Fariyal Jamadar | Day 14 | Performance Defect | Sprint 3 | Fariyal J | Maintainability | Slow response or delay in processing | Day 15 | Closed | isssue resolved
16 | Fariyal Jamadar | Day 16 | False fraud detection | Sprint 4 | Fariyal J | User Interface | Tuned ML model and adjusted threshold | Day 17 | Closed | issue resolved
17 | Fariyal Jamadar | Day 18 | Dashboard issue | Sprint 5 | Fariyal J | Maintainability | Fixed bugs and improved real-time data sync | Day 20 | Closed | issue resolved
Dashboard layout not loading properly on smaller screens
18 | SIDDINENI GOPALA KRISHNA | DAY 1 | Dashboard layout not loading properly on smaller screens | Sprint 1 | SIDDINENI GOPALA KRISHNA | USER INTERFACE | Fixed CSS Grid and flexbox | Day 2 | Closed | Layout loads correctlty
19 | SIDDINENI GOPALA KRISHNA | DAY 2 | Dark mode not loading after refresh | Sprint 1 | SIDDINENI GOPALA KRISHNA | LOGICAL | Added localstorage persistence | Day 3 | Closed | Dark mode loads correctly
20 | SIDDINENI GOPALA KRISHNA | DAY 3 | Weather widget causing page not loading | Sprint 1 | SIDDINENI GOPALA KRISHNA | User Interface | Removed widget from slidebar | Day 3 | Closed | Page loads without issues
21 | SIDDINENI GOPALA KRISHNA | DAY 4 | RISK BUTTONS NOT LOADING IN GRID | sprint 2 | SIDDINENI GOPALA KRISHNA | User Interface | created 3 x 2 CSS GRID | DAY 4 | Closed | BUTTONS LOAD IN CORRECT LAYOUT
22 | G.Lohitha | DAY 1 | data preprocessing | sprint 1 | G.Lohitha |  | Cleaned dataset | Day 6 | closed | issue resolved
23 | G.Lohitha | Day 12 | Functional Defect | sprint 2 | G.Lohitha | Logical | OCR fails | Day 13 | closed | issue resolved
24 | G.Lohitha | Day14 | Performance Defect | Sprint 3 | G.Lohitha | Maintainability | Slow response or delay in processing | Day 15 | closed | issue resolved
25 | G.Lohitha | Day 16 | False fraud detection | sprint 4 | G.Lohitha | user interface | Tuned ML model and adjusted threshold | Day 17 | closed | issue resolved
26 | G.Lohitha | Day 18 | Dashboard issue | sprint 5 | G.Lohitha | Maintainability | Fixed bugs and improved real-time data sync | Day 20 | closed | issue resolved
27 | SIDDINENI GOPALA KRISHNA | DAY 5 | PROFILE DATA NOT LOADING IN MODEL | sprint 2 | SIDDINENI GOPALA KRISHNA | Logical | added localstorage user fetch | Day 7 | Closed | profile data loads correctly
28 | SIDDINENI GOPALA KRISHNA | DAY 8 | analytics charts are not loading | sprint 2 | SIDDINENI GOPALA KRISHNA | Logical | integrated chart is library | Day 10 | Closed | charts loads with animations
29 | SIDDINENI GOPALA KRISHNA | Day 10 | document page not loading on click | sprint 2 | SIDDINENI GOPALA KRISHNA | User Interface | fixed sidebar navigation links | Day 11 | Closed | navigation loads currently
30 | SIDDINENI GOPALA KRISHNA | Day 12 | button animations not loading | Sprint 3 | SIDDINENI GOPALA KRISHNA | User Interface | added css keyframe animations | Day 15 | Closed | animations load on hover
31 | SIDDINENI GOPALA KRISHNA | Day 16 | mobile view not loading properly | Sprint 3 | SIDDINENI GOPALA KRISHNA | Maintainability | added media queries | Day 17 | Closed | mobile layout loads correctly
32 | Tanuja V | DAY 1 | data preprocessing | sprint 1 | Tanuja V | Logical | Cleaned dataset | Day 6 | closed | issue resolved
33 | Tanuja V | Day 12 | Functional Defect | sprint 2 | Tanuja V | Logical | OCR fails | Day 13 | closed | issue resolved
34 | Tanuja V | Day14 | Performance Defect | Sprint 3 | Tanuja V | Maintainability | Slow response or delay in processing | Day 15 | closed | issue resolved
35 | Tanuja V | Day 16 | False fraud detection | sprint 4 | Tanuja V | user interface | Tuned ML model and adjusted threshold | Day 17 | closed | issue resolved
36 | Tanuja V | Day 18 | Dashboard issue | sprint 5 | Tanuja V | Maintainability | Fixed bugs and improved real-time data sync | Day 20 | closed | issue resolved

## Sheet2
Logical
User Interface
Maintainability
Standards
Data
Performance
Others